## WBS
Phase | ID | Task | Priority | Status | Est. Hours | Depends On | Notes
Phase 0 - Discovery & Requirements | P0-1 | Analyse company website & current digital process | Must | Done | 3 |  | Found: manual triage, no case tracking, no document management, no system of record
Phase 0 - Discovery & Requirements | P0-2 | Review existing SMSSA-fe CRM repository | Must | Done | 4 |  | Mapped real pages/components (ClientPortal, CorporateDashboard, DocumentChecklistView, etc.)
Phase 0 - Discovery & Requirements | P0-3 | Confirm local dev environment runs | Must | Done | 1 | P0-2 | npm install / npm run dev / npm run build all verified
Phase 0 - Discovery & Requirements | P0-4 | Interview IT manager on CRM integration approach | Must | Done | 2 |  | Confirmed: build AI layer around existing CRM, not a replacement
Phase 0 - Discovery & Requirements | P0-5 | Confirm CRM API/webhook availability with IT manager | Must | To Do | 2 | P0-4 | Determines integration Path A vs Path B
Phase 0 - Discovery & Requirements | P0-6 | Draft functional & non-functional requirements document | Must | To Do | 6 | P0-1,P0-2
Phase 0 - Discovery & Requirements | P0-7 | Get client sign-off on requirements | Must | To Do | 2 | P0-6 | Needs a real email/meeting + written confirmation
Phase 1 - Architecture & Design | P1-1 | System architecture diagram | Must | To Do | 4 | P0-5 | FE, REST API, AI layer, CRM connector, mobile
Phase 1 - Architecture & Design | P1-2 | Entity-Relationship (ER) diagram | Must | To Do | 5 | P0-5 | Full database schema, dbdiagram.io/Lucidchart
Phase 1 - Architecture & Design | P1-3 | UML Class diagram | Must | To Do | 4 | P1-2
Phase 1 - Architecture & Design | P1-4 | UML Sequence diagram - Login/Registration flow | Must | To Do | 3 | P1-3
Phase 1 - Architecture & Design | P1-5 | UML Sequence diagram - AI Intake Triage flow | Must | To Do | 3 | P1-3
Phase 1 - Architecture & Design | P1-6 | Draft OpenAPI/Swagger contract | Should | To Do | 5 | P1-1 | Spec for new AI-layer endpoints
Phase 2 - Backend & AI Agent Layer | P2-1 | Scaffold backend REST API project | Must | To Do | 4 | P1-1
Phase 2 - Backend & AI Agent Layer | P2-2 | Build CRM Integration Connector | Must | To Do | 10 | P0-5,P2-1 | Path A (direct API) or Path B (companion DB)
Phase 2 - Backend & AI Agent Layer | P2-3 | Implement Intake Triage Agent | Must | To Do | 8 | P2-2
Phase 2 - Backend & AI Agent Layer | P2-4 | Implement Document Checklist Agent | Must | To Do | 8 | P2-2
Phase 2 - Backend & AI Agent Layer | P2-5 | Implement Eligibility Pre-Screening Agent | Should | To Do | 8 | P2-2 | Non-binding output only
Phase 2 - Backend & AI Agent Layer | P2-6 | Implement Case Status / Client Chatbot Agent | Must | To Do | 8 | P2-2
Phase 2 - Backend & AI Agent Layer | P2-7 | Implement Consultant Summarisation Agent | Should | To Do | 6 | P2-2
Phase 2 - Backend & AI Agent Layer | P2-8 | Implement Visa/Permit Expiry & Renewal Agent | Should | To Do | 6 | P2-2
Phase 2 - Backend & AI Agent Layer | P2-9 | Implement Interview/Consulate Prep Chatbot | Could | To Do | 6 | P2-2
Phase 2 - Backend & AI Agent Layer | P2-10 | Implement AI fallback logic | Must | To Do | 5 | P2-3,P2-4 | Reverts to structured form fields if AI unavailable
Phase 2 - Backend & AI Agent Layer | P2-11 | Publish API documentation | Must | To Do | 4 | P1-6 | Swagger UI or Postman collection
Phase 3 - Frontend Integration | P3-1 | Add AI chatbot widget to ClientPortalView | Must | To Do | 6 | P2-6
Phase 3 - Frontend Integration | P3-2 | Wire Document Checklist Agent into DocumentChecklistView | Must | To Do | 5 | P2-4
Phase 3 - Frontend Integration | P3-3 | Add expiry/renewal alerts to DashboardView | Should | To Do | 4 | P2-8
Phase 3 - Frontend Integration | P3-4 | Add interview prep chatbot entry point | Could | To Do | 4 | P2-9
Phase 3 - Frontend Integration | P3-5 | Fix mobile responsiveness | Should | To Do | 8 |  | Known existing gap flagged in prior commit history
Phase 4 - Additional Service Modules | P4-1 | Tax module - document extraction agent | Could | To Do | 6 | P2-2
Phase 4 - Additional Service Modules | P4-2 | Tax module - residency/gap agent | Could | To Do | 6 | P4-1
Phase 4 - Additional Service Modules | P4-3 | Tax module - clearance submission agent | Could | To Do | 6 | P4-2 | Requires practitioner sign-off before submission
Phase 4 - Additional Service Modules | P4-4 | Wills module - estate intake agent | Could | To Do | 6 | P2-2
Phase 4 - Additional Service Modules | P4-5 | Wills module - will drafting agent | Could | To Do | 6 | P4-4
Phase 4 - Additional Service Modules | P4-6 | Wills module - execution compliance checklist agent | Could | To Do | 5 | P4-5 | Requires attorney sign-off before execution
Phase 5 - Mobile App | P5-1 | Scaffold mobile app project | Should | To Do | 5 | P2-11
Phase 5 - Mobile App | P5-2 | Implement case status screen | Should | To Do | 6 | P5-1
Phase 5 - Mobile App | P5-3 | Implement document upload | Should | To Do | 6 | P5-1 | Camera + file upload
Phase 5 - Mobile App | P5-4 | Implement consultant/chatbot messaging | Should | To Do | 6 | P5-1,P2-6
Phase 6 - QA & Compliance | P6-1 | Write formal test plan | Must | To Do | 5 | P0-6
Phase 6 - QA & Compliance | P6-2 | Execute manual test cases | Must | To Do | 8 | P6-1 | Log expected vs actual results
Phase 6 - QA & Compliance | P6-3 | Draft POPIA-aware Terms of Use / Privacy Note | Must | To Do | 4 | P0-6
Phase 6 - QA & Compliance | P6-4 | Security review | Must | To Do | 4 | P2-2 | API key handling, role-based access, audit trail
Phase 7 - Client Handoff | P7-1 | Write short user guide | Must | To Do | 4 | P6-2 | Admin, Consultant, and Client roles
Phase 7 - Client Handoff | P7-2 | Final demo & client sign-off | Must | To Do | 3 | P7-1,P6-2
Phase 7 - Client Handoff | P7-3 | Deployment & handoff documentation | Must | To Do | 4 | P7-2

## Summary
Phase | Total Tasks | Done | To Do | % Complete | Total Est. Hours
Phase 0 - Discovery & Requirements | 7 | 4 | 3 | 57.14% | 20
Phase 1 - Architecture & Design | 6 | 0 | 6 | 0% | 24
Phase 2 - Backend & AI Agent Layer | 11 | 0 | 11 | 0% | 73
Phase 3 - Frontend Integration | 5 | 0 | 5 | 0% | 27
Phase 4 - Additional Service Modules | 6 | 0 | 6 | 0% | 35
Phase 5 - Mobile App | 4 | 0 | 4 | 0% | 23
Phase 6 - QA & Compliance | 4 | 0 | 4 | 0% | 21
Phase 7 - Client Handoff | 3 | 0 | 3 | 0% | 11
TOTAL | 46 | 4 | 42 | 8.696% | 234